## minassah-sprint2
WBS | PO, QA mail | Task | Description | Estimated Start Date | Calendar Days | Estimated Ready On | Write Progress | Task is | Resources email | Write Estimated Hours | Actual Hour | Cost | 2015-04-10 | 2015-04-11 | 2015-04-12 | 2015-04-13 | 2015-04-14 | 2015-04-15 | 2015-04-16 | 2015-04-17 | 2015-04-18 | 2015-04-19 | 2015-04-20 | 2015-04-21 | 2015-04-22 | 2015-04-23 | 2015-04-24 | 2015-04-25 | 2015-04-26 | 2015-04-27 | 2015-04-28 | 2015-04-29 | 2015-04-30 | 2015-05-01 | 2015-05-02 | 2015-05-03 | 2015-05-04 | 2015-05-05 | 2015-05-06 | 2015-05-07 | 2015-05-08 | 2015-05-09 | 2015-05-10 | 2015-05-11 | 2015-05-12 | 2015-05-13 | 2015-05-14 | 2015-05-15 | 2015-05-16 | 2015-05-17 | 2015-05-18 | 2015-05-19 | 2015-05-20 | 2015-05-21 | 2015-05-22 | 2015-05-23 | 2015-05-24 | 2015-05-25 | 2015-05-26 | 2015-05-27 | 2015-05-28 | 2015-05-29 | 2015-05-30 | 2015-05-31 | 2015-06-01 | 2015-06-02 | 2015-06-03 | 2015-06-04 | 2015-06-05 | 2015-06-06 | 2015-06-07 | 2015-06-08 | 2015-06-09 | 2015-06-10 | 2015-06-11 | 2015-06-12 | 2015-06-13 | 2015-06-14 | 2015-06-15 | 2015-06-16 | 2015-06-17 | 2015-06-18 | 2015-06-19 | 2015-06-20
http://www.timeanddate.com/date/workdays.html?y1=2015&m34914322=4&d34914441=17&y2=2015&m34914754=4&d34914873=17
1 | anil@clickapps.co,m.bajaber@clickapps.co | Manage my portfolio |  | 2015-04-13 | 37.5 | 20-May-15 | 106% | Independent | chetan@clickappsco.com, anil@clickappsco.com, akhil@clickappsco.com, varun@clickappsco.com, amitoj@clickappsco.com, a.kumar@clickappsco.com | 232.0 | 379 | Rs75,800.00
1.1 | anil@clickapps.co | Req. Understanding Analysis,Queries | detail about task | 2015-04-13 | 1 | 14-Apr-15 | 1% | Independent | chetan@clickappsco.com, anil@clickappsco.com, akhil@clickappsco.com, varun@clickappsco.com, amitoj@clickappsco.com, a.kumar@clickappsco.com | 5 | 6 | Rs1,200.00 |  |  |  | 4 | [10 empty] | 2
1.2 | anil@clickapps.co | R&D | Details | 2015-04-11 | 1 | 12-Apr-15 | 20% | Independent |  | 0 | 18 | Rs3,600.00 | [11 empty] | 4 |  | 4 | 3 |  |  |  | 4 |  | 3
1.3 | anil@clickapps.co,m.bajaber@clickapps.co | UI Task 1 | Create Profile | 2015-04-14 | 1 | 15-Apr-15 | 100% | Complete | amitoj@clickapps.co | 10 | 8 | Rs1,600.00 |  |  |  |  | 8
1.4 | anil@clickapps.co,m.bajaber@clickapps.co | UI Task 2 | Create Portofio | 2015-04-14 | 1 | 15-Apr-15 | 100% | Complete | amitoj@clickapps.co | 8 | 3 | Rs600.00 |  |  |  |  | 3
1.5 | anil@clickapps.co,m.bajaber@clickapps.co | Dev task 1 | Manage categories - Admin side | 2015-04-14 | 1 | 15-Apr-15 | 100% | Independent | akhil@clickapps.co | 3 | 3 | Rs600.00 |  |  |  |  | 3
1.6 | anil@clickapps.co,m.bajaber@clickapps.co | UI Task 3 | Category Forms | 2015-04-15 | 1 | 16-Apr-15 | 100% | Independent | amitoj@clickapps.co | 8 | 8 | Rs1,600.00 | [5 empty] | 8
1.7 | anil@clickapps.co,m.bajaber@clickapps.co | Dev task 2 | Rnd on Video player | 2015-04-15 | 1 | 16-Apr-15 | 100% | Independent | akhil@clickapps.co | 4 | 4 | Rs800.00 | [5 empty] | 4
1.8 |  | Dev task 3 | Link form with categories - Admin side | 2015-04-16 | 1 | 17-Apr-15 | 100% | Dependant | akhil@clickapps.co | 16 | 16 | Rs3,200.00 | [6 empty] | 8 | 8
1.9 | anil@clickapps.co,m.bajaber@clickapps.co | Dev task 4 | Database Design for Porfolio | 2015-04-15 | 1 | 16-Apr-15 | 100% | Complete | varun@clickapps.co | 3 | 3 | Rs600.00 | [5 empty] | 3
1.10 |  | Dev task 5 | Create portfolio | 2015-04-20 | 8.5 | 28-Apr-15 | 99% | Dependant | akhil@clickapps.co | 55 | 96 | Rs19,200.00 | [10 empty] | 8 | 4 | 8 | 4 | 3 |  |  | 6 | 4 | 8 | 5 | 8 |  |  | 8 | 6 | 8 | 8 |  |  |  |  | 8
1.11 | anil@clickapps.co,m.bajaber@clickapps.co | UI Task 4 | Discover page listing | 2015-04-17 | 1 | 18-Apr-15 | 90% | Independent | amitoj@clickapps.co | 8 | 7 | Rs1,400.00 | [7 empty] | 7
1.12 |  | UI Task | Refinement of Design Elements and work on manageportfolio page | 2015-04-27 | 5 | 2-May-15 | 70% |  |  | 16 | 15 | [18 empty] | 7.5 | 7.5
1.14 |  | UI Task | Crop Portfolio popup setting | 2015-04-29 | 1 | 30-Apr-15 |  |  |  | 16 | 14 | [20 empty] | 7 | 7
1.13 |  | QA Testing | functional,ui test en version | 2015-05-11 | 7 | 18-May-15 |  | Dependant |  | 40 | 44 | [32 empty] | 4 | 6 | 6 | 6 | 5 | 5 |  |  | 6 | 6
1.14 | anil@clickapps.co,m.bajaber@clickapps.co | Dev - en to ar conversion | manage portfolio, searching page | 2015-05-11 | 3 | 14-May-15 |  | Dependant | akhil@clickapps.co | 0 | 88 | Rs17,600.00 | [10 empty] | 8 | 4 | 8 | 4 | 3 |  |  | 6 | 4 | 8 | 5 | 8 |  |  | 8 | 6 | 8 | 8
1.13 |  | QA Testing | functional,ui test ar version | 2015-05-19 | 3 | 22-May-15 |  | DependentOn |  | 40 | 15 | [48 empty] | 5 | 5 | 5
1.14 | anil@clickapps.co,m.bajaber@clickapps.co | Comment moderation |  |  |  |  | 90% | Independent | akhil@clickapps.co |  | 8 | [35 empty] | 8
1.14 | anil@clickapps.co,m.bajaber@clickapps.co | Managing categories attachment type from admin |  |  |  |  | 100% | Independent | akhil@clickapps.co |  | 16 | [35 empty] | 8 |  |  |  |  | 8
[11 empty] | 0 | Rs0.00
2 | anil@clickapps.co,m.bajaber@clickapps.co | Filter user listing display in the page | Details | 2015-03-10 | 0 | 10-Mar-15 | 0% | Independent |  | 0.0 | 0 | Rs0.00
2.1 |  | Req. Understanding Analysis,Queries | detail about task | 2015-04-10 | 0 | 10-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
2.2 |  | R&D | Details | 2015-04-11 | 0 | 11-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
2.3 |  | UI Task | Details | 2015-04-12 | 0 | 12-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
2.4 |  | Dev task1 | Details | 2015-04-13 | 0 | 13-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
2.5 |  | Dev task2 | Details | 2015-04-14 | 0 | 14-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
2.6 |  | QA Testing | Details | 2015-04-15 | 0 | 15-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
2.7 |  | Bug Fix UI | Details | 2015-04-16 | 0 | 16-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
2.8 |  | Bug Fix Dev | Details | 2015-04-17 | 0 | 17-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
2.9 |  | QA Regression | Details | 2015-04-18 | 0 | 18-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
2.10 |  | PM Review | Details | 2015-04-19 | 0 | 19-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
[8 empty] | Independent |  |  | 0 | Rs0.00
3 | anil@clickapps.co,m.bajaber@clickapps.co | Sort user listing in the page | Details | 2015-03-10 | 1 | 11-Mar-15 | 0% | Independent |  | 0.0 | 0 | Rs0.00
3.1 |  | Req. Understanding Analysis,Queries | detail about task | 2015-04-10 | 0.5 | 10-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
3.2 |  | R&D | Details | 2015-04-11 | 0.5 | 11-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
3.3 |  | UI Task | Details | 2015-04-12 | 0 | 12-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
3.4 |  | Dev task1 | Details | 2015-04-13 | 0 | 13-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
3.5 |  | Dev task2 | Details | 2015-04-14 | 0 | 14-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
3.6 |  | QA Testing | Details | 2015-04-15 | 0 | 15-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
3.7 |  | Bug Fix UI | Details | 2015-04-16 | 0 | 16-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
3.8 |  | Bug Fix Dev | Details | 2015-04-17 | 0 | 17-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
3.9 |  | QA Regression | Details | 2015-04-18 | 0 | 18-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
3.10 |  | PM Review | Details | 2015-04-19 | 0 | 19-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
[8 empty] | Independent |  |  | 0 | Rs0.00
4 | anil@clickappsco.com | Do advanced search for users | Details | 2015-03-10 | 1 | 11-Mar-15 | 0% | Independent |  | 0.0 | 0 | Rs0.00
4.1 |  | Req. Understanding Analysis,Queries | detail about task | 2015-04-10 | 0.5 | 10-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
4.2 |  | R&D | Details | 2015-04-11 | 0.5 | 11-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
4.3 |  | UI Task | Details | 2015-04-12 | 0 | 12-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
4.4 |  | Dev task1 | Details | 2015-04-13 | 0 | 13-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
4.5 |  | Dev task2 | Details | 2015-04-14 | 0 | 14-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
4.6 |  | QA Testing | Details | 2015-04-15 | 0 | 15-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
4.7 |  | Bug Fix UI | Details | 2015-04-16 | 0 | 16-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
4.8 |  | Bug Fix Dev | Details | 2015-04-17 | 0 | 17-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
4.9 |  | QA Regression | Details | 2015-04-18 | 0 | 18-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
4.10 |  | PM Review | Details | 2015-04-19 | 0 | 19-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
[8 empty] | Independent |  |  | 0 | Rs0.00
5 | anil@clickappsco.com | Mark any profile | Details | 2015-03-10 | 1 | 11-Mar-15 | 0% | Independent |  | 8.0 | 0 | Rs0.00
5.1 |  | Req. Understanding Analysis,Queries | detail about task | 2015-04-10 | 0.5 | 10-Apr-15 |  | Independent |  | 8 | 0 | Rs0.00
5.2 |  | R&D | Details | 2015-04-11 | 0.5 | 11-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
5.3 |  | UI Task | Details | 2015-04-12 | 0 | 12-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
5.4 |  | Dev task1 | Details | 2015-04-13 | 0 | 13-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
5.5 |  | Dev task2 | Details | 2015-04-14 | 0 | 14-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
5.6 |  | QA Testing | Details | 2015-04-15 | 0 | 15-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
5.7 |  | Bug Fix UI | Details | 2015-04-16 | 0 | 16-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
5.8 |  | Bug Fix Dev | Details | 2015-04-17 | 0 | 17-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
5.9 |  | QA Regression | Details | 2015-04-18 | 0 | 18-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
5.10 |  | PM Review | Details | 2015-04-19 | 0 | 19-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
[8 empty] | Independent |  |  | 0 | Rs0.00
6 | anil@clickappsco.com | Unmark any profile | Details | 2015-03-10 | 1 | 11-Mar-15 | 0% | Independent |  | 0.0 | 0 | Rs0.00
6.1 |  | Req. Understanding Analysis,Queries | detail about task | 2015-04-10 | 0.5 | 10-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
6.2 |  | R&D | Details | 2015-04-11 | 0.5 | 11-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
6.3 |  | UI Task | Details | 2015-04-12 | 0 | 12-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
6.4 |  | Dev task1 | Details | 2015-04-13 | 0 | 13-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
6.5 |  | Dev task2 | Details | 2015-04-14 | 0 | 14-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
6.6 |  | QA Testing | Details | 2015-04-15 | 0 | 15-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
6.7 |  | Bug Fix UI | Details | 2015-04-16 | 0 | 16-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
6.8 |  | Bug Fix Dev | Details | 2015-04-17 | 0 | 17-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
6.9 |  | QA Regression | Details | 2015-04-18 | 0 | 18-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
6.10 |  | PM Review | Details | 2015-04-19 | 0 | 19-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
[8 empty] | Independent |  |  | 0 | Rs0.00
7 | anil@clickappsco.com | Rate any profile | Details | 2015-03-10 | 1 | 11-Mar-15 | 0% | Independent |  | 8.0 | 0 | Rs0.00
7.1 |  | Req. Understanding Analysis,Queries | detail about task | 2015-04-10 | 0.5 | 10-Apr-15 |  | Independent |  | 8 | 0 | Rs0.00
7.2 |  | R&D | Details | 2015-04-11 | 0.5 | 11-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
7.3 |  | UI Task | Details | 2015-04-12 | 0 | 12-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
7.4 |  | Dev task1 | Details | 2015-04-13 | 0 | 13-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
7.5 |  | Dev task2 | Details | 2015-04-14 | 0 | 14-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
7.6 |  | QA Testing | Details | 2015-04-15 | 0 | 15-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
7.7 |  | Bug Fix UI | Details | 2015-04-16 | 0 | 16-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
7.8 |  | Bug Fix Dev | Details | 2015-04-17 | 0 | 17-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
7.9 |  | QA Regression | Details | 2015-04-18 | 0 | 18-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
7.10 |  | PM Review | Details | 2015-04-19 | 0 | 19-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
[8 empty] | Independent |  |  | 0 | Rs0.00
8 | anil@clickappsco.com | Mark any project | Details | 2015-03-10 | 1 | 11-Mar-15 | 0% | Independent |  | 8.0 | 0 | Rs0.00
8.1 |  | Req. Understanding Analysis,Queries | detail about task | 2015-04-10 | 0.5 | 10-Apr-15 |  | Independent |  | 8 | 0 | Rs0.00
8.2 |  | R&D | Details | 2015-04-11 | 0.5 | 11-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
8.3 |  | UI Task | Details | 2015-04-12 | 0 | 12-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
8.4 |  | Dev task1 | Details | 2015-04-13 | 0 | 13-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
8.5 |  | Dev task2 | Details | 2015-04-14 | 0 | 14-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
8.6 |  | QA Testing | Details | 2015-04-15 | 0 | 15-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
8.7 |  | Bug Fix UI | Details | 2015-04-16 | 0 | 16-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
8.8 |  | Bug Fix Dev | Details | 2015-04-17 | 0 | 17-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
8.9 |  | QA Regression | Details | 2015-04-18 | 0 | 18-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
8.10 |  | PM Review | Details | 2015-04-19 | 0 | 19-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
Independent
9 | anil@clickappsco.com | Unmark any project | Details | 2015-03-10 | 1 | 11-Mar-15 | 0% | Independent |  | 8.0 | 0 | Rs0.00
9.1 |  | Req. Understanding Analysis,Queries | detail about task | 2015-04-10 | 0.5 | 10-Apr-15 |  | Independent |  | 8 | 0 | Rs0.00
9.2 |  | R&D | Details | 2015-04-11 | 0.5 | 11-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
9.3 |  | UI Task | Details | 2015-04-12 | 0 | 12-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
9.4 |  | Dev task1 | Details | 2015-04-13 | 0 | 13-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
9.5 |  | Dev task2 | Details | 2015-04-14 | 0 | 14-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
9.6 |  | QA Testing | Details | 2015-04-15 | 0 | 15-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
9.7 |  | Bug Fix UI | Details | 2015-04-16 | 0 | 16-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
9.8 |  | Bug Fix Dev | Details | 2015-04-17 | 0 | 17-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
9.9 |  | QA Regression | Details | 2015-04-18 | 0 | 18-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
9.10 |  | PM Review | Details | 2015-04-19 | 0 | 19-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
Independent
10 | anil@clickappsco.com | Like any project | Details | 2015-03-10 | 1 | 11-Mar-15 | 0% | Independent |  | 8.0 | 0 | Rs0.00
10.1 |  | Req. Understanding Analysis,Queries | detail about task | 2015-04-10 | 0.5 | 10-Apr-15 |  | Independent |  | 8 | 0 | Rs0.00
10.2 |  | R&D | Details | 2015-04-11 | 0.5 | 11-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
10.3 |  | UI Task | Details | 2015-04-12 | 0 | 12-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
10.4 |  | Dev task1 | Details | 2015-04-13 | 0 | 13-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
10.5 |  | Dev task2 | Details | 2015-04-14 | 0 | 14-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
10.6 |  | QA Testing | Details | 2015-04-15 | 0 | 15-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
10.7 |  | Bug Fix UI | Details | 2015-04-16 | 0 | 16-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
10.8 |  | Bug Fix Dev | Details | 2015-04-17 | 0 | 17-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
10.9 |  | QA Regression | Details | 2015-04-18 | 0 | 18-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
10.10 |  | PM Review | Details | 2015-04-19 | 0 | 19-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
Independent
11 | anil@clickappsco.com | admin: Create Categories (differnet types of Minassah) | Details | 2015-03-10 | 1 | 11-Mar-15 | 0% | Independent |  | 8.0 | 0 | Rs0.00
11.1 |  | Req. Understanding Analysis,Queries | detail about task | 2015-04-10 | 0.5 | 10-Apr-15 |  | Independent |  | 8 | 0 | Rs0.00
11.2 |  | R&D | Details | 2015-04-11 | 0.5 | 11-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
11.3 |  | UI Task | Details | 2015-04-12 | 0 | 12-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
11.4 |  | Dev task1 | Details | 2015-04-13 | 0 | 13-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
11.5 |  | Dev task2 | Details | 2015-04-14 | 0 | 14-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
11.6 |  | QA Testing | Details | 2015-04-15 | 0 | 15-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
11.7 |  | Bug Fix UI | Details | 2015-04-16 | 0 | 16-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
11.8 |  | Bug Fix Dev | Details | 2015-04-17 | 0 | 17-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
11.9 |  | QA Regression | Details | 2015-04-18 | 0 | 18-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
11.10 |  | PM Review | Details | 2015-04-19 | 0 | 19-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
Independent
12 | anil@clickappsco.com | admin: Enable / disable comments moderation for the comment in the user profiles page | Details | 2015-03-10 | 1 | 11-Mar-15 | 0% | Independent |  | 28.0 | 0 | Rs0.00
12.1 |  | Req. Understanding Analysis,Queries | detail about task | 2015-04-10 | 0.5 | 10-Apr-15 |  | Independent |  | 8 | 0 | Rs0.00
12.2 |  | R&D | Details | 2015-04-11 | 0.5 | 11-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
12.3 |  | UI Task | UI Refinement | 2015-04-23 | 0 | 23-Apr-15 |  | Independent |  | 20 | 7 | Rs1,400.00 | [13 empty] | 7
12.4 |  | Dev task1 | Details | 2015-04-13 | 0 | 13-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
12.5 |  | Dev task2 | Details | 2015-04-14 | 0 | 14-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
12.6 |  | QA Testing | Details | 2015-04-15 | 0 | 15-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
12.7 |  | Bug Fix UI | Details | 2015-04-16 | 0 | 16-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
12.8 |  | Bug Fix Dev | Details | 2015-04-17 | 0 | 17-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
12.9 |  | QA Regression | Details | 2015-04-18 | 0 | 18-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
12.10 |  | PM Review | Details | 2015-04-19 | 0 | 19-Apr-15 |  | Independent |  | 0 | 0 | Rs0.00
Independent
Independent
Independent
Independent
Independent
Independent
Independent
Independent
Independent
Independent
Independent
Independent
Independent
Independent
Independent
Independent
Independent
Independent
Independent
Independent
Independent
Independent
Independent
Independent
Independent

## Releases
Releases | Sprint | Date | Section |  | Dev Team Hr | Comments
2 | 1 | 2015-04-14 | 1. Create and Manage categories | ADMIN SIDE
2 | 1 | 2015-04-15 | 2. Create / Edit Portfolio | UI SIDE
2 | 1 | 2015-04-16 | 3. My Portfolio | UI SIDE
2 | 1 | 2015-04-17 | 4. Db Design and Rnd on Mixit up Jquery | DEV SIDE
2 | 2 | 2015-04-20
2 | 2 | 2015-04-21
2 | 2 | 2015-04-22
2 | 2 | 2015-04-23
2 | 2 | 2015-04-24
2 | 2 | 2015-04-27
2 | 2 | 2015-04-28
2 |  | 2015-04-29
2 |  | 2015-04-30
2 |  | 2015-05-01
Done

## Resources
Resource name | Type | Rate per resource | Total count | Total cost
resource | type | rate | count | cost
work

## sprint1
| M.Ali | Minnasah (For internal team purpose)
[5 empty] | 2015-03-09 | [6 empty] | 2015-03-16 | [6 empty] | 2015-03-23 | [6 empty] | 2015-03-30 | [6 empty] | 2015-04-06 | [6 empty] | 2015-04-13 | [6 empty] | 2015-04-20 | [6 empty] | 2015-04-27
Build version |  | Backlog Item | Est. Hours | Actual | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
[19 empty] | 3 |  |  |  | 5 |  |  | 1.5 | 4 | 7 | 7
B1 | Talent | Register in the system |  | 0
|  | UI | 5 | 0
|  | Dev | 8 | 0
|  | QA | 4 | 0
B1 | Talent | Verify my account |  | 0
|  | UI | 2 | 0
|  | Dev |  | 0
|  | QA | 2 | 0
| Talent | Create My Profile |  | 0
|  | UI | 7 | 0
|  | Dev |  | 0
|  | QA | 4 | 0
| Talent | Edit My profile info |  | 0
|  | UI | 5 | 0
|  | Dev |  | 0
|  | QA | 4 | 0
B1 | Scout | Register in the System |  | 0
|  | UI | 2 | 0
|  | Dev |  | 0
|  | QA | 4 | 0
B1 | Scout | Verify My account |  | 0
|  | UI | 2 | 0
|  | Dev |  | 0
|  | QA | 2 | 0
| Scout | Create My profile |  | 0
|  | UI | 4 | 0
|  | Dev |  | 0
|  | QA | 4 | 0
| Scout | Edit My profile info |  | 0
|  | UI | 4 | 0
|  | Dev |  | 0
|  | QA | 4 | 0
B1 | Scout , Talent | Retrieve My User name and password |  | 0
|  | UI | 2 | 0
|  | Dev |  | 0
|  | QA | 1 | 0
B1 | Scout , Talent | See the listing for all users In the System |  | 0
|  | UI | 7 | 0
|  | Dev |  | 0
|  | QA | 4 | 0
| Scout , Talent | Search for a specific user by name "Simple search" |  | 0
|  | UI | 5 | 0
|  | Dev |  | 0
|  | QA | 2 | 0
| Scout , Talent | See users profile details |  | 0
|  | UI | 5 | 0
|  | Dev |  | 0
|  | QA | 4 | 0
Development
Testing